## Slide 1: MEASURES TO BE TAKEN AT DESIGN STAGE FOR IMPROVING QUALITY GATED PROCESS
Anirban Ghosh
Senior Manager- Quality Assurance
CAIRN INDIA LIMITED

## Slide 3: GATED PROCESS:
Gated process is fundamental to the way Cairn brings major Capital developments to commercial operation.
It is a process to establish Governance and Control check points to provide specific and consistent metrics so that all projects are judged objectively and rigorously.
Gated process ensures that all aspects of the development in question align in terms of reservoir/ resource development, engineering maturity, approvals and other stake holder requirements are met with all key assurance activities and reviews identified and undertaken.

## Slide 4: GATED PROCESS:
From conceptualization to Decommissioning, the whole review process have been divided into Seven different Phases. Each phase is called “A Gate”. Specific Check Lists are prepared with regard to each GATE and audits are conducted at each stage. Audit observations, depending upon the severity category are needed to be closed appropriately prior to move on to next level of activities.

## Slide 5: GATED PROCESS:
Note : PHSER (PROJECT HSEQ REVIEW) CYCLE
PHSER - I
Exploration &
Appraisal
PHSER – II
Development
PHSER – III
Design
PHSER – IV
Construction
PHSER – V
Pre- Commissioning
PHSER – VI
Start-up
PHSER - VII
Abandonment /
De-Commissioning
Engineering, Quality, HSE, Projects, Legal Assurance
Engineering, Quality, HSE, Projects
Engineering, Quality, HSE, Projects
Engineering, Quality, HSE, Projects, Operation
Engineering, Quality, HSE,
Projects, Operation,
Asset Integrity
G&G, Petroleum Engineering, HSE, Quality, Legal Assurance
G&G, Petroleum Engineering, HSE, Quality, Legal Assurance

## Slide 6: GATED PROCESS:
Explore
1
Appraise
2
Assess / Select
3
Define
4
Execute
5
Operate
Stage Gate Plan
Exploration Manager establishes stage gate plan for the specific investment.
Development Manager updates the stage gate plan for Gate – 2, Gate – 3 and Gate – 4a
Discovery
Commerciality
Concept Select
6
Sanction
3a
4a
Stage Gate Plan
RFSU
PIA
6–12 Months
Project Manager updates the stage gate plan for Project for Gate – 4 and Gate – 5
Stage Gate Plan
Asset Manager updates the stage gate plan and closes it out after project investment review (Gate -6)
Stage Gate Plan

## Slide 7: GATED PROCESS:
Explore
1
Appraise
2
Assess / Select
3
Define
4
Execute
5
Operate
Discovery
Commerciality
Concept Select
6
Sanction
RFSU
PIA
6–12 Months
3a
4a
Exploration activities, Seismic, Well Testing, Drilling Etc.,
Field Development Planning
Feasibility Studies
Pre-Engg.
FEED
Drilling / Well Completion
Detailed Design
Procurement
Construction
Commissioning
Start-up
Approved, Detailed Exploration Work Program & Budget
Appraisal strategy & program
Field Development Plan
Building facilities & Hand over to Operation
De-commissioning plan, Execution and Env. impact
SOP’s for actual performance Vs. business proposal
Certification to build up facilities

## Slide 8
Thorough Review of each Stage by panel experts
All recommendations are appraised at a particular stage only
A transparent governance is established
Helps Timely Completion of Projects
Instantly addressing technical queries, deviation
Helps assuring a qualitative quotient with the stake holders
GATED PROCESS: - Advantages

## Slide 9
Put together all panel experts at the same time.
Constituting a competent bench strength for the activity.
Timely closure of all the observations.
Prevention of repetitive re-occurrence.
GATED PROCESS: - Challenges

## Slide 10
A well planned schedule in Advance
Empowerment on respective Gate Keepers
Engaging Consultants
Lesson Learnt data base for reference
GATED PROCESS: - Mitigation to the Challenges :

## Slide 11
Assuring the proper material, welding and NDT procedures at the design stage itself
Adhering the recommendations of the Jaipur and Hazira Fire Incidents in design
Ensuring Implementation of requirements from codes, standards, specifications
Compliance to all regulatory and legal requirements
Ensuring proper utility coverage of critical equipments and instruments
Benefits reaped through GATED Process:

## Slide 12
Thank You